## Sheet1
Week / Task | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20 | Week21 | Week22 | Week23 | Week24 | Week25 | Week26 | Week27 | Week28 | Week29 | Week30 | Week31 | Week32 | Week33 | Week34 | Week35 | Week36 | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44
| 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11
Study on ANC and Theory | bar: Week1
Synchronizing Speakers | bar: Week1 to Week2
Do the Literature review | bar: Week2 to Week3
Simulate ANC in matlab or Python | bar: Week4 to Week5
Develop architecture of the whole algorithm | bar: Week5 to Week7
Start Hardware Prototyping | Week8: Mid Semester Break
Finish the setup architecture and test | bar: Week9 to Week10
ANC implementation | bar: Week11 to Week13
Test ANC with drone noise | bar: Week13 to Week14
Integrate with multiple speakers | Week17: Exam Semester 7
Make a full prototype | bar: Week22 to Week24
Do the power optimization and Payload optimization | bar: Week25 to Week27
Test in the environement | bar: Week26 to Week30
Optimize overall performance with drone | bar: Week29 to Week32
Make the final product | bar: Week33 to Week34
Test the Final Device | bar: Week35 to Week38
Research Paper Writing and final Review | bar: Week39 to Week44